## Sheet1
Meeting Objectives | Meeting Agenda | Actions to be taken after the meeting | Action Owner | Meeting Attendees
1. Review the current project status and progress made since the last meeting. | 1. Project Status Update: Review completed tasks, ongoing work, and any obstacles encountered. | 1. Mahmoud to update the project board with the latest status and priorities. | Mahmoud | Mahmoud (Software Team Lead)
2. Discuss and prioritize the remaining tasks for the current sprint. | 2. Sprint Backlog Review: Evaluate the progress of user stories in the current sprint backlog. | 2. Ahmed to begin work on the highest-priority user stories in the sprint backlog. | Ahmed | Ahmed (Software Developer)
3. Identify any blockers or challenges hindering progress. | 3. Task Prioritization: Prioritize remaining user stories and tasks based on project goals and deadlines. | 3. Mohamed to review and update test cases for the completed user stories. | Mohamed | Mohamed (Software Tester)
4. Plan and allocate resources for upcoming tasks and sprints. | 4. Blocker Discussion: Identify any blockers or challenges impeding progress and brainstorm solutions. | 4. Mahmoud to communicate with stakeholders about any identified blockers and proposed solutions. | Mahmoud
5. Confirm understanding and alignment on project goals and expectations. | 5. Resource Planning: Allocate resources, including team members and tools, for upcoming tasks and sprints. | 5. Ahmed to provide regular updates on progress during daily stand-up meetings. | Ahmed
|  | 6. Mohamed to conduct thorough regression testing before the sprint review. | Mohamed
|  | 7. Ahmed and Mohamed to collaborate closely on user story implementation and testing. | Ahmed and Mohamed
|  | 8. Mahmoud to schedule a mid-sprint review meeting to assess progress and make adjustments if needed. | Mahmoud
|  | 9. All team members to ensure documentation is kept up-to-date and accessible. | All team members