## Sheet1
Epic | User Story | Priority | Ready to be Planned | Planned Sprint | Status
User Authentication and Account Management | As a user, I want to create an account | High | Yes | Sprint 1 | In Progress
User Authentication and Account Management | As a user, I want to login to my account | High | Yes | Sprint 1 | In Progress
User Authentication and Account Management | As a user, I want to logout securely | High | Yes | Sprint 1 | In Progress
Browsing and Searching | As a user, I want to view restaurants | High | Yes | Sprint 1 | In Progress
Browsing and Searching | As a user, I want to search for restaurants | Medium | Yes | Sprint 2 | Not Started
Restaurant Interaction | As a user, I want to view the menu of a restaurant | High | Yes | Sprint 1 | In Progress
Restaurant Interaction | As a user, I want to add items to my cart | High | Yes | Sprint 1 | In Progress
Order Management | As a user, I want to purchase items in my cart | High | Yes | Sprint 1 | In Progress
Order Management | As a user, I want to view my order history | Medium | Yes | Sprint 2 | Not Started
Order Management | As a user, I want to leave reviews for restaurants | Medium | Yes | Sprint 2 | Not Started
Order Management | As a user, I want to mark orders as delivered | Medium | Yes | Sprint 2 | Not Started
Customer Service Admin Control | As a user, I want to assign customer service admins | High | Yes | Sprint 3 | Not Started
Customer Service Admin Control | As a user, I want to view and manage customer queries | High | Yes | Sprint 3 | Not Started
Customer Service Admin Control | As a user, I want to resolve customer issues | High | Yes | Sprint 3 | Not Started
Delivery Management | As a user, I want to track my order delivery status | Medium | Yes | Sprint 2 | Not Started
Delivery Management | As a user, I want to schedule delivery time | Medium | Yes | Sprint 2 | Not Started
Payment Options | As a user, I want to choose from multiple payment methods | High | Yes | Sprint 2 | Not Started
Payment Options | As a user, I want to apply discount codes | Medium | Yes | Sprint 2 | Not Started
Localization | As a user, I want the app to be available in multiple languages | Medium | Yes | Sprint 3 | Not Started
Localization | As a user, I want to set my preferred language | Low | Yes | Sprint 3 | Not Started